## Sheet1
DEFECT TRACKING LOG
Project Name | PHPtravels Website
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause
1 | 27/10/2022 | RAMYA.N | Flight Link is not clickable in supplier dashboard |  | Testing | H |  | / | / | / | / | / | /
2 | 27/10/2023 | RAMYA.N | Visa modules is not displayed in supplier dashboard and clickable |  | Testing | H |  | / | / | / | / | / | /
3 | 20/10/2022 | RAMYA.N | Display message "Your booking status is ( Pending ) and payment status is Pay Later ( Unpaid )" eventhough the payment is done sucessfully.Many invoices shows this wrong message. |  | Testing | H |  | / | / | / | / | / | /
4 | 26/10/2022 | RAMYA.N | The phptravels.net and its modules shows alert messages regarding xml every time the page is loaded |  | Testing | H |  | / | / | / | / | / | /
5 | 21/10/2022 | RAMYA.N | The admin login page shows "wrong Credential" message eventhough the correct username and password is given. |  | Testing | H |  | / | / | / | / | / | /
6 | 18/10/2022 | RAMYA.N | phptravels.net website frequently shows timeoout message |  | Testing | H |  | / | / | / | / | / | /
7 | 2022-03-11 | RAMYA.N | When Booking link is clicked in supplier page, it is not redirecting to booking page..instead its shows "An Error Was Encountered" |  | Testing | H |  | / | / | / | / | / | /